Children Education Programme

POPI

Monthly  Progress Report

Month: October 2010

Result-1: Children have access to Early Childhood Development (ECD) Programme

| Activity | Target | Achieve | Deviation | Remarks |
| --- | --- | --- | --- | --- |
| 1.1.1) Nr of ECD centers established | - | - | - | 20 ECD centers were established in January 2010 against the target of 20. |
| 1.1.2) Nr of children enrolled | - | - | - | 665 (362 boys and 303 girls) children were enrolled in 20 ECD centers in January 2010. In October 2010, 01 child was dropped out due replaced to an orphanage because of his father death. 664 (361 boys and 303 girls) are continuing now. |
| 1.1.3) Drop out rate reduced | 3% | - | - | 01 dropped out. |
| 1.1.4) % of average attendance of children increased | 97% | 97% | - |  |
| # of students assessment | 664 | 664 | - |  |
| % of students assessment | 100% | 100% |  |  |
| 1.1.5) Nr of trained teachers on ECD | 20 | 18 | 02 | 02 teachers did not receive basic training due to recent recruitment. |
| # of drop out teachers in ECD | - | - |  | No teacher dropped out in this month. |
| 1.1.6) Nr of participants aware about child right issue through P/meeting | 664 | 496 | 268 | ECD of Atkapara and Parikharpar did not held parents meeting. |
| Nr of parents meeting organized | 20 | 18 | 02 | Do |
| Nr of parents attend in parents meeting | 664 | 496 | 268 |  |
| % of average attendance in parents meeting | 100% | 75% | 25% |  |

Result-2: Children have access to Primary Education Organized by POPI

| Activity | Target | Achieve | Deviation | Remarks |
| --- | --- | --- | --- | --- |
| 1.2.1) Nr of Primary schools established | - | - | - | 06 Formal primary schools were established in January 2010 against the target 06. |
| 1.2.2) Nr of children enrolled | - | - | - | 943 children were enrolled in 06 FPS in January 2010 against the target of 900. 07 children dropped out and 01 child admitted. 937 (469 boys and 468 girls) children are continuing now. |
| 1.2.3) Drop out rate reduced | 4% | - | - | 0.6% drop out occurred during this time. |
| 1.2.4) % of average attendance of children increased | 96% | 93% | 3% |  |
| # of students assessment | 937 | 891 | 46 | Teachers did not assessed 35 children of S Salua school, 03 children of Pultakandi, 03 children of F.M. Alam and 05 children in Md. Ali school due to their absence. The teachers were advised to take assessment of those children. |
| % of students assessment | 100% | 95% | 5% |  |
| 1.2.5) Nr of trained teachers on Primary education | 24 | 21 | 03 | 02 teachers did not receive basic training due to recent recruitment and 01 teacher due to sickness. |
| # of drop out teachers | - | - | - | No teacher dropped out in this month. |
| # of refreshers training organized | 01 | 01 | - |  |
| # of attendance in refreshers meeting | 24 | 24 | - |  |
| 1.2.6) Nr of children promoted to next class | - | - | - | Not applicable for this month. |
| 1.2.7) Nr of children completed primary education | - | - | - | Not applicable for this month. |
| 1.2.8) Nr of participants aware about child right issue through P/meeting | 359 | 319 | 30 |  |
| Nr of parents meeting organized | 6 | 6 | - |  |
| Nr of parents attend in parents meeting | 359 | 319 | 40 |  |
| % of average attendance in parents meeting | 100% | 89% | 11% |  |
| # of SMC meeting | 03 | 03 | - |  |
| Nr of participants in meeting | 36 | 26 | 10 |  |
| % of average attendance in SMC meeting | 100% | 72% | 28% |  |
| 1.2.9) Nr of SMC members trained of child rights | 18 | - | - | According to the project proposal, we have to conduct training for SMC members during this year. We have a plan to conduct this training on November 2010. |
| 1.2.10) Nr of schools received donation of land from community people | - | - | - | We already received donation of land from 05 schools and received lease from railway department for 01 school. |
| # of school getting first letter for registration from primary education department | - | - | - | We got 1st letter for registration from primary education department against the schools of Mirerchar and Pultakandi. |
| # of school getting 2nd letter for registration from primary education department | - | - | - | We are waiting for 2nd letter during this year. |
| # of land processing | - | - | - | For 06 schools, land processing has been completed. |

Result-3: Children have access to Community and Registered Primary Schools

| Activity | Target | Achieve | Deviation | Remarks |
| --- | --- | --- | --- | --- |
| 1.3.1) Nr of community and registered primary schools supported | - | - | - | From January 2010, 10 community and registered primary school were supported. |
| 1.3.2) Nr of children enrolled | - | - | - | In January 2010, 3153 children were enrolled in 10 community and registered primary schools. 03 children were dropped out. In September 2010, 08 children were enrolled in 02 primary schools. 3158 (1561 boys and 1597 girls) children are continuing now. |
| 1.3.3) Drop out rate reduced | 15% | - | - | 03 children dropped out during the reporting period and that is 0.0009% of total children. |
| 1.3.4) % of average attendance of children increased | 85% | 86% | - |  |
| # of students assessment | 3158 | 2697 | 461 |  |
| % of students assessment | 100% | 85% | 15% |  |
| 1.3.5) Nr of children promoted to next classes | - | - | - | Not applicable for this month. |
| 1.3.6) Nr of children completed primary school | - | - | - | Not applicable for this month. |
| 1.3.7) Nr of trained teachers on primary education | - | - | - | Not applicable for this month. |
| Nr of drop out teacher from CPS/RPS | 0 | 0 | 0 | No drop out occurred in this month. |
| Nr of organized refreshers training for teachers | 0 | 0 | 0 | No target in this month. |
| Nr of participants in refreshers training | - | - | - | Do |
| 1.3.8) Nr of participants aware of child rights through parents teacher meeting | 496 | 354 | 142 |  |
| Nr of parents meeting organized | 10 | 09 | 01 | Meeting did not organized in Farirogunathpur primary school. |
| Nr of participants in parents meeting | 496 | 354 | 142 |  |
| % of average attendance | 100% | 71% | 29% |  |
| Nr of SMC meeting organized | 10 | 10 | nil |  |
| Nr of participants in SMC meeting | 120 | 88 | 32 |  |
| % of average attendance | 100% | 73% | 27% |  |
| 1.3.9) Nr of SMC members trained of child rights | 30 | 36 | - | We have conducted training for 36 SMC members of 04 primary schools. |

Result-4: Orphan Children have access to Education

| Activity | Target | Achieve | Deviation | Remarks |
| --- | --- | --- | --- | --- |
| 1.4.1) Nr of children enrolled in orphanage | - | - | - | In January 2010, 55 children were enrolled in Orphanage against the target of 55. 54 children are continuing now. |
| 1.4.2) Nr of children enrolled in primary school | - | - | - | 36 children were enrolled in primary school against the target of 22. |
| Nr of children enrolled in ECD | - | - | - | 11 children were enrolled in ECD in January 2010. |
| 1.4.3) Nr of children enrolled in secondary | - | - | - | 19 children were enrolled in secondary school against the target of 33. 01 student dropped out. 18 children are continuing now. |
| # of drop out students | - | - | - | 01 student dropped out during January to July 2010. |
| % of average attendance | 99% | 99.69% | - |  |
| # of students assessment | 54 | 43 | 11 | Assessment was not taken for ECD children. |
| Nr of students teachers meeting | 01 | 01 | - |  |
| Nr of participants in meeting | 54 | 53 | 01 |  |
| 1.4.4) Nr of children promoted to next class | - | - | - | Not applicable for this month. |
| 1.4.5) Nr of children completed primary education | - | - | - | Not applicable for this month. |
| 1.4.6) Nr of children completed secondary education | - | - | - | Not applicable for this month. |
| 1.4.7) Nr of children received shelter, food and non food items | 55 | 54 | 01 | 01 student left out the orphanage. |